Proposed Timeline for 2005 Conference, hosted by Unity Church–Unitarian, St. Paul, Local Arrangements

Summer 2003		Compare hotel sites/costs

November 2003	Sign hotel contract

Summer 2004		Put together conference budget

Create conference “logo”

Recruit co-chairs

July 2004		Meet with Conference Program Committee

August 1, 2004		Mailing for workshop presenters to church leaders

(directed by Program Committee)

August 2004		Preliminary budget to Program Coordinator for consultation

Draft budget to PSD Board for approval (8/27 – 28)

Article to PSD for the September issue of The Prairie Star

(deadline: 8/23)

September 2004	8.5 x 11 poster for churches to post – to PSD office

Electronic version of poster for PSD website w/reduced-size

version for PSD website for church newsletter editors

October 2004		Meet with Conference Program Committee

Draft of registration brochure to PSD Program Coordinator for

feedback

Recruit volunteers

Firm number of meeting rooms to hotel by November 1

November 2004	Registration brochure to PSD office for approval

Final budget to PSD Board for approval (11/12 – 13)

Continue recruiting volunteers

December 2004		Brochure to Sarah Greene at PSD office

Submit conference promotion to PSD newsletter

On-line registration ready

January 2005		Meet with Conference Program Committee

Hotel team to select meals

Mail brochure to individuals and congregations

(deadline: 1/14)

March 2005		Registration early deadline: March 1

April 8-10, 2005	Annual conference

Revised: 11-15-04