FUS Local Arrangements Committee

Principal Functions

- Select conference hotel and negotiate contract, then recommend budget and registration fee for conference (1-2 people)

- Create a conference logo. Then create a conference brochure, including registration form (1-2 people)

- Mail over 2000 copies of brochure (Either paid for or 5-7 one day volunteers)

- Conduct on-going conference publicity to member congregations (chair)

- Assemble registration packets and name tags for attendees. Staff registration table and offer on-site greeters (6 people)

- Handle conference registration forms and funds (including workshop registrations, meal tallies, coordinating roommate requests, and home housing) (2 people)

- Serve as treasurer to handle accounting for income and disbursements (1 person)

- Arrange Saturday night entertainment (1-2 people)

- Conduct 1-2 small evening worship services and 1 large Sunday morning one (2-3 people)

- Serve as liaison with hotel (meal counts, menu selections, space needs, audio-visual needs, table set-ups, signage, etc.) (1-2 people, could be same as #1)

- Plan day care for children ages 0-4 yrs throughout conference (1 person)

- Plan space needs for children 5-12 yrs throughout conference (1 person)

- Develop inventory for and staff conference bookstore at the hotel throughout conference (1-2 people)

- Arrange display area at hotel and manage registration for individuals and groups seeking display space (1-2 people, could be same as #13)

- Organize banner parade and accompanying music, plus banner display after parade is over (2 people)

- Organize table topics (1 person)

- Recruit Master (or Mistress?) of Ceremonies (1 person)

- Aesthetics (1 person)

- Maintain records for guidance to future PSD Local Arrangements Committees (Chair)

Total participation needed: 26 – 40 people