ANNUAL CONFERENCE PROGRAM COMMITTEE

MINUTES

October 23, 2004

PRESENT:  Sam Wormley - Chair, Eric Severson, Gina Dugan, Maura Williams (05 Local)

MINUTES TO:  Barbara Hubbard, Elaine Rockwell, Julie Handberg, Mary Amundson, Mildred Larson, Nancy Heege, Phillip Lund, Sarah Greene, Suzanne Owens-Pike.

CHECK IN – small group today!

AGENDA REVIEW – Agenda approved

REVIEW MINUTES OF JULY 17, 2004 – Minutes approved

WORKSHOPS 2005

Lengthy discussion of workshop tracks and the placement of workshops into time slots A, B, C.

Categories emerged: Justice/Outreach; Community; Worship/Music/Arts/Creativity; History, Intergenerational; Leadership; Resources; Unity/Diversity; Other.

The Labyrinth was made into an activity offering throughout the day rather than a workshop.  Brainstormed ideas for a historical tour of Unity Church and showing of documentary film into the conference schedule.

*Eric: Clarify workshop #24 with Karen Wille and communicate with Phil Lund about Youth/Adult Fishbowl.

*Maura: Contact Labyrinth team for size specifics

Conference Schedule:

Workshop A – 10:30-11:45am

Workshop B – 1:30-2:45pm

Workshop C – 3:00-4:15pm

Business meeting 1.5 hours, 4:30-6:00pm

Social hour – 6:00-7:00pm

Banquet – 7:00pm

REVIEW OF PROGRESS – 2005 CONFERENCE (April 8-10)

Barbara Hubbard provided an update from Local Arrangements:

- Unity team leaders have been identified

- Recruitment for committees begins tomorrow.

- Choir

- Table Topics

- Ribbons for delegates. See Sarah Greene

- Registration packets

- Refreshments/Breaks

- Banner parade/hanging of banners during conference

- Exhibitors – flat fee for exhibit space

- Bookstore

- Meals - Friday meal is up to local arrangements

- Registration online

*Question:  Ask Nancy about reception for DRE’s and RE Directors and Friends of PSD

BROCHURE DEADLINE – MONDAY OCTOBER 25

*Eric: Any workshop corrections go directly to Maura Williams prior to brochure deadline.

*Eric: Confirmation letters to workshop presenters.

NEXT MEETING DATE

Winter meeting tbd, January or early February. 10:00 AM – 2:00 PM

Recorded by Gina Dugan